## Migrated Data
ID | FutureNow Ticket | External ID | ARE | Created On | Due by | Reported By | Message Processor | Last Changed on | Last Changed By | Priority | Status | Description
| INC44051042 |  | STSPL IN | 05.11.25 |  | T, Purushothama |  | 2025-12-20 |  | 3 - Medium | Confirm_Closed | #HC Image in VIM Workplace not showing up
| INC44013959 |  | BUZ | 2025-11-05 |  | Bara, Claudia Mihaela |  | 2025-12-19 |  | 2 - High | Confirm_Closed | hc:workflow invoices cannot be forwarded
| INC44053998 |  | gen | 05.11.25 |  | Šplíchalová, Ilona |  | 2025-12-19 |  | 4 - Low | Confirm_Closed | Forward issue
| INC44138662 |  | gen | 2025-11-17 20:22 |  | Cajtchamlová, Martina |  | 2025-12-17 |  | 2 - High | In Process | issue after R1421 - system still reports, that user is processing PO
| INC44198641 |  | gen | 2025-11-24 14:46 |  | Cajtchamlová, Martina |  | 2025-12-15 |  | 4 - Low | Confirm_Closed | VIM_close the process and move documents to "My Completed" tab
| INC44236544 |  | 3366 WSTECH | 2025-11-28 10:10 |  | Rupp, Christine |  | 2025-12-17 |  | 4 - Low | Confirm_Closed | Please introduce rounding acceptance for WSTECH - 3366
| INC44247780 |  | 3003 | 2025-12-01 |  | Cífka, Zdeněk |  | 2025-12-16 |  | 3 - Medium | Confirm_Closed | S4P / 3003 - Payment block Z is automatically entered in RD documents after making any change through the transaction FBD3
| INC44262323 |  | STSPL IN | 2025-12-02 |  | T, Purushothama |  | 2025-12-17 |  | 4 - Low | Confirm_Closed | Posted invoices are not being directed to the correct approvers
| INC44276638 |  | BUZ | 2025-12-04 06:29 |  | Foghis, Loredana Daniela |  | 2025-12-15 |  | 3 - Medium | Confirm_Closed | cannot approve doc ID 26179
| INC44300907 |  | gen | 2025-12-08 10:31 |  | Integration User |  | 2025-12-15 |  | 3 - Medium | Confirm_Closed | Document approval not in my inbox
| INC44300914 |  | BUZ | 2025-12-08 10:31 |  | Geis, Martina |  | 2025-12-19 |  | 4 - Low | Confirm_Closed | Cannot forward invoice to several colleagues
| INC44320339 |  | SMO DK | 2025-12-10 14:14 |  | Piedade, Pedro |  | 2025-12-16 |  | 3 - Medium | Confirm_Closed | NPO Credit notes not able to post
| INC44329030 |  | SMO DK | 2025-12-11 |  | Høy, Niels-Erik |  | 2025-12-17 |  | 3 - Medium | Confirm_Closed | My Inbox invoices
| INC44335466 |  | gen | 2025-12-12 14:19 |  | Nemec, Martina |  | 2025-12-15 |  | 4 - Low | Confirm_Closed | Add 3 suppliers to VIM VAUD table to stop autoposting
| INC44338252 |  | BUZ | 2025-12-14 14:11 |  | Cajtchamlová, Martina |  | 2025-12-15 |  | 4 - Low | Confirm_Closed | VIM_please remove R block if possible and close the process
| INC44338461 |  | BUZ | 2025-12-14 18:21 |  | Cajtchamlová, Martina |  | 2025-12-18 |  | 4 - Low | Confirm_Closed | VIM_no agent assigned to uncomplete documents
| INC44338463 |  | BUZ | 2025-12-14 18:25 |  | Cajtchamlová, Martina |  | 2025-12-15 |  | 4 - Low | Confirm_Closed | VIM_uncompleted documents moved to All completed
| INC44339355 |  | STSPL IN | 2025-12-15 04:33 |  | V, Anand |  | 2025-12-15 |  | 4 - Low | Confirm_Closed | #HC VIM OCR Access Required
| INC44343292 |  | BUZ | 2025-12-15 11:15 |  | Bara, Claudia Mihaela |  | 2025-12-19 |  | 2 - High | Confirm_Closed | Invoices are not available in App "approval invoices" only in "my inbox"
| INC44344891 |  | gen | 2025-12-15 14:03 |  | Šplíchalová, Ilona |  | 2025-12-17 |  | 3 - Medium | Confirm_Closed | Missing in Exception app + no authorisation
| INC44345852 |  | BUZ | 2025-12-15 16:01 |  | Kostovski, Simon |  | 2025-12-18 |  | 3 - Medium | Confirm_Closed | Approval cannot be started
| INC44345935 |  | BUZ | 2025-12-15 |  | Cajtchamlová, Martina |  | 2025-12-16 |  | 4 - Low | Confirm_Closed | VIM_DP 16243 - close the process
| INC44345961 |  | BUZ | 2025-12-15 |  | Kostovski, Simon |  | 2025-12-15 |  | 2 - High | In Process | Customs invoices approval did not start, even though the Approvers are set in the SATtable
| INC44346255 |  | BUZ | 2025-12-15 |  | Kostovski, Simon |  | 2025-12-23 |  | 2 - High | In Process XXflagXX | Please remove payment blocks, items cannot be paid
| INC44351758 |  | SMO DK | 2025-12-16 |  | Piedade, Pedro |  | 2025-12-22 |  | 3 - Medium | In Process XXflagXX | PDF Invoices don't appear in VIM Documents
| INC44352220 |  | SMO DK | 2025-12-16 |  | Piedade, Pedro |  | 2025-12-16 |  | 3 - Medium | In Process | Document is with error in Analytics but I can't see it in Workplace
| INC44352828 |  | BUZ | 2025-12-16 |  | Helici, Lucica |  | 2025-12-23 |  | 4 - Low | In Process XXflagXX | PDF not available for invoice to be approved
| INC44354118 |  | gen | 2025-12-16 |  | Nemec, Martina |  | 2025-12-17 |  | 4 - Low | Confirm_Closed | Add one supplier into VIM VAUD table
| INC44355232 |  | BUZ | 2025-12-16 |  | Cajtchamlová, Martina |  | 2025-12-17 |  | 4 - Low | Confirm_Closed | VIM_close process and remove R block
| INC44359287 |  | BUZ | 2025-12-17 |  | Cajtchamlová, Martina |  | 2025-12-17 |  | 4 - Low | Confirm_Closed | add vendor 1000034952 to the table to allow posting with multiple POs
| INC44359840 |  | BUZ | 2025-12-17 |  | Cajtchamlová, Martina |  | 2025-12-17 |  | 4 - Low | Confirm_Closed | remove payment block and close the process
| INC44361127 |  | 3366 WSTECH | 2025-12-17 |  | Munk, Monika |  | 2025-12-22 |  | 3 - Medium | In Process XXflagXX | Multiple occurences of this issue. Not VIM-related. AUN 3366 - in VIM pdf-Belege Invoice nicht sichtbar wg. fehlerhafter Download-Anzeige
| INC44362368 |  | SMO DK | 2025-12-17 |  | Jensen, Bettina W. |  | 2025-12-17 |  | 3 - Medium | In Process | INC44207813 closed, documentation attached to this inc
| INC44363749 |  | SMO DK | 2025-12-17 |  | Piedade, Pedro |  | 2025-12-17 |  | 3 - Medium | Confirm_Closed | Cannot work on the VIM item altough it says blocked
| INC44368543 |  | BUZ | 2025-12-18 |  | Cajtchamlová, Martina |  | 2025-12-18 |  | 3 - Medium | In Process | no agent assigned to DP 33621
| INC44369987 |  | BUZ | 2025-12-18 |  | Maresi Alina Corina |  | 2025-12-23 |  | 3 - Medium | In Process XXflagXX | in the App "Approval invoice management" - the invoice is not visible
| INC44370593 |  | BUZ | 2025-12-18 |  | Ilic, Isabelle |  | 2025-12-18 |  | 3 - Medium | In Process | Incoming Invoices FX Exchange Rate Issue - System using wrong date for whole 3014
| INC44371083 |  | BUZ | 2025-12-18 |  | Cajtchamlová, Martina |  | 2025-12-18 |  | 4 - Low | In Process | VIM_Status Cancelled vs. different statuses
| INC44371201 |  | BUZ | 2025-12-18 |  | Cajtchamlová, Martina |  | 2025-12-18 |  | 4 - Low | In Process | VIM_Status Blocked vs. Posted
| INC44371312 |  | gen | 2025-12-18 |  | Cajtchamlová, Martina |  | 2025-12-18 |  | 4 - Low | In Process | Hide the "Rescan" button in VIM Indexing screen
| INC44371487 |  | gen | 2025-12-18 |  | Cajtchamlová, Martina |  | 2025-12-18 |  | 4 - Low | In Process | change predefined reversal reason in VIM
| INC44372855 |  | STSPL IN | 2025-12-19 |  | D R, Thirumalegowda |  | 2025-12-19 |  | 4 - Low | In Process | # HC VIM Workplace, the GST Registration Number is getting updated, and the Business Place is auto-changing unexpectedly
| INC44377414 |  | BUZ | 2025-12-19 |  | Cedidlo, Jiří |  | 2025-12-22 |  | 4 - Low | In Process XXflagXX | Document unblocking
| INC44380098 |  | BUZ | 2025-12-21 |  | Cajtchamlová, Martina |  | 2025-12-22 |  | 4 - Low | In Process XXflagXX | add vendor 1000019241 to the table to allow posting with multiple POs

## New Entries
ID | FutureNow Ticket | External ID | ARE | Created On | Due by | Reported By | Message Processor | Last Changed on | Last Changed By | Priority | Status | Description
No data available